FOURTH  SIX-MONTHLY PERIODIC REPORT

FIFTH  SIX-MONTHLY PERIODIC REPORT

SIXTH  SIX-MONTHLY PERIODIC REPORT

In an integrated form

Front page

- Full name of the Centre of Excellence

Számítástechnikai és Automatizálási Kutató Intézet MTA SZTAKI

Computer and Automation Institute, Hungarian Academy of Sciences

(Address: Budapest, Kende utca 13-17. Hungary H-1111,)

Telephone:+36-1-2796224  fax:+36-1-4667503 email: haidegger@sztaki.hu

- Report title: The  forth, fifth and sixth six-monthly periodic report

- Reporting period:  from 01. September, 2002 to 28. February, 2003

from 01.  March, 2003 to 31. August, 2003

from 01. September, 203 to 29 February, 2004

- Report’s last version issued on:   16. May  2004

- Contract number:  ICA1-CT-2000-70025

- Project start date and duration: 1. March, 2001 for 3 years +10 months

- EU funding:  600 000 Euros

- Project title: Technology and Science for the Information Society,  Institute SZTAKI as a Centre of Excellence

- Acronym:  HUN-TING

- Keywords: Computer Science & Control, Information & Communication Technology,  Intelligent Automation

- Name of the Co-ordinator:  Dr. Géza  Haidegger

Activity progress report

MTA SZTAKI was fulfilling its scientific tasks basically as much as possible according to the submitted plans and to the accepted contract version. We invited, selected and hosted foreign research experts to work with our colleagues on various themes related to our activities. We had the chance to visit other institutions and deepen our co-operation with international scientific partners. We have been very active in international co-operation, and thanks to the prestigious title of Centre of Excellence, we had achieved nice results in research and in forming joint activities, preparing joint 5th and 6th Framework proposals, etc.

In period #4, we had 4 professors/scientists   to work with us,

In period #5, we had 4 professors, one in overlap with period #3,

In period #6,  we had 6 professors, one in overlap with period #5.

We have planned, organised, prepared and conducted several workshops and conferences. They were successful both for us, organisers, and also for all participants. Our Institute’s national and international appreciation has been raised by these actions. We are proud to have organised:

Data GRID workshop and Workshop on Supercomputing at Piliscsaba

We participated at the Control Exhibition in Budapest, and held several  information days for the promotion of  the 6th Framework launch. Large amount of  EU information materials were  collected at the Opening of the 6th Framework  conference in Brussels  and distributed among the Hungarian participants of the meetings.

During the  5th period,  one of our  greatest action was the organization of the World-Wide-Web  International  Conference with 570 participants. But we are proud also to have hosted the following  further seminars and workshops:

An IFAC  IMS  Workshop on Intelligent Manufacturing, with 60,

The DCFS 2003, with 52 participants,

The IFAC Workshop on Control Applications,

The ERCIM WG Conference on Constrains,

International GRID Seminar in March-April,

SW Technology and Distributed Systems, 2nd April,

CBSNet workshop,  on 3-4 April ,

MACHTECH exhibition and  EU R&D Workshop, dedicated to industrial machine industry, visitors 3000,  participants 34

Two e-learning fora, ( in March and June) with a growing participation (90—110 participants)

A Technology Assesment meeting in July ,

A GRID Tutorial in June ,

During the 6th period, the largest Conference we organized was the World Science Forum, 8-10. November 2003, with 450 participants. This was probably the largest scientific international event in Hungary during  2003.

We had  good feedback on the IST and Quality  Management Forum and on the APART2 GRID event,  organized at Rackeve, 11-13.  November.

In the end of February, we had a successful workshop devoted to connect innovative Hungarian SME-s  to SME partners in Sweden. The 2 days long workshop allowed both scientific  and market-oriented  discussions among Hungarian and Swedish  participants.

According to the plans, our laboratories utilised the previously purchased durable equipment (hardware and software) in order to meet the requirements of research co-operation envisaged.

Just to list briefly some key areas:

7 significant science books were published by authors of our Institute, on Cellular Neural Networks, Visual Computing, Process Modelling and Model Analysis,  Intelligent Control Systems, On Non-linear Systems with Varying Structures.

12 books have been edited by  SZTAKI researchers, and the long list of    publications are given in the attachment.

Out of this number, 57 publications appeared in international journals, 69 within international co-operation. Almost 120 oral conference presentations were carried out.  7 new Ph.D. degrees were granted and 2 titles for Doctor of Academy were received.  53 scientists had taken part in lecturing at university courses.

Almost 30 projects had been contracted and being worked on within the 5th Framework Programme of the EU..

By the Launch of the 6th Framework Programme  our Institute had a good start. We had submitted   around 50 proposals,  and  the plans are also very impressive, to  keep up this rate.  Regarding the success rate of the  6th Framework proposals, we are  falling behind the  previous figures, but still, can be proud to have  contracted several ones rather soon.  A full list of submitted  and accepted proposals  is available, but is not  shown in  public domain   documents.

(At the time of last edition, this figure is as:

Number of submitted proposals:   21,  number of accepted:   7 )

Our Institute, due to its devoted scientific area of Automation and Computer Sciences, has a special role and   value:  MTA SZTAKI is the Hungarian key institute in the ERCIM Society.  (European Research Consortium for Information and Mathematics)  (www.ercim.org). This membership in the consortium  offers MTA SZTAKI to  find the best  scientific partners in Europe, and through an active participation in the actions of ERCIM,  MTA SZTAKI  can better disseminate its scientific results, while  opens the doors also to  attract young international scientists.  This channel had proven to be very valuable to recruit those professors, scientists and Ph.D. fellows that promoted the many joint work and proposal we could develop.

The participation of the key researchers and of the directors of MTA SZTAKI within the Directors’ Meeting and the Executive Committee meetings plus at the Working Group meetings are very essential. Several of the CoE   scientific progress results are related to the ERCIM actions.  The director and the deputy director of MTA SZTAKI regularly take part at the ERCIM top-level meetings, and several key researchers are working in  special ERCIM scientific working groups.

The travels and visits from MTA SZTAKI to other European research entities are mostly financed by separate sources, and just a few are managed through the CoE  program. As it can be seen from the yearly reports, around  300 travels are managed yearly for the scientific cooperation among  the European partners and our Institute.

During the last periods, we had the following visits to European partners based on the CoE:

Establishing the RENED Network of Scientific Cooperation – in Sofia-December 2002,

Maintaining the membership in the OSACA Network of “Open systems in Controls”, - Stuttgart University, December 2002,

Virtual joint laboratory and Department  initiative – twinning- with the Klagenfurt /Austria University, - started in 2001-2001-, Dec. 2003,

EUREKA  cooperation within the FACTORY Umbrella ,  a cluster to generate successful  NMP and IST – IMS  proposals-    a meeting in Edindurgh-2001-Oct, a meeting in   Hague, 2002-May,  a meeting in  Thessaloniki -2002 Oct,  and a meeting in SupsiManno- 2003 November.  Already several 6th Framework Proposals were prepared based on the EUREKA Factory Umbrella cooperation.

Virtual laboratories are being developed and operated.  It took us several semesters to harmonise the requirements among various participants.

Virtual laboratories are to be very essential for the future, and MTA SZTAKI is working on extending its present   ties.  The most developed Virtual Laboratory had been developed by the (WP6-7)  Manufacturing Automation  entities of MTA SZTAKI, built around the  former cooperation with the Stuttgart Fraunhofer Institute (FhG IPA).  Other virtual Laboratory developments are underway with: several universities in France, England,  Germany, Austria, Rumania and  Italy. We also initiated a closer cooperation framework with other Centres of Excellences, and by the end of the project, we will be pleased to report on many plans reached as success.

Workpackage progress report for Workpackage No.: A

Project Management and co-ordination

- Objectives and planned actions:

The objectives were to direct and co-ordinate all activities to successfully meet the goals of the Centre. From the beginning, all our actions have been influenced by the general and specific aims of the EU, through the Centre of Excellence programme.

- Problems encountered:

Some visitors, who agreed to  join our institute, had to postpone or had to cancel their visit. The 11th of September  had a very strong negative effect on business travels, and  research topics and priorities were  altered.

The coordinator  had some personal problem, and thus, the reporting to the Project Officer had been delayed significantly. By now, the  main obstacles are  eliminated, and there are no foreseen problems till the end of the planned project (December 2004).

- Results:

We have defined the specific financial processes and their handling mechanism for all foreseen CoE activities.

- Publications and papers:

We have participated,  actively organized and delivered  training courses and workshops for promoting EU 5th + EU 6th  Framework actions,  and on preparing proposals.

- Deliverables:

- D.A.1 Increased  networking among centres

There is a significant increase in networking and cooperation. A detailed list of cooperation channels  for each thematic group or laboratory is given in the appended sections.

- D.A.2 Increased, -enhanced FP participation

There were a significant increase in the FP5 participation, and   a list of the  30 + successful FP5 projects is detailed in the appended section.

- Periodic reports.

Yearly reports of MTA SZTAKI  is appended. – for 2002, and for 2003. Separate sections are for the list of yearly publications, and for the citations.

Workpackage progress report for Workpackage No.: B

Exploitation and dissemination, twinning and multimedia/videoconferencing system to support co-operation

- Objectives and planned actions:

The objectives are to make the best use of the visiting scientists’ stay, and to gain benefits from their visits. By implementing video-conferencing and new equipment for multimedia, we planned to introduce the most up-to-date technology for assisting these activities.

.

- Problems encountered:

Videoconferencing was not yet accepted by many  partners from industry, due to  the relatively un-sharp motion pictures  and  noisy sound effects.

By the replacement of equipment to new, high-bandwidths systems, the situation has changed, and  now we are having more and more  conferences that we can   stream – distribute via the internet.  The IP-based communication   facilities had been enhanced  to allow high-bandwidth connections.

- Results:

We have implemented a video-conferencing environment for accessing international channels with high bandwidth.  We organised and participated in several video-conferencing events, and invited industrial partners to  join us  within those events.

We are constantly documenting our scientific events on digital media, and the slides, photos and video-recordings are  archived.

We have prepared posters and slide-shows for demonstrating our Centre of Excellence at numerous exhibitions, at universities when trying to attract young undergraduates, graduates  and postgraduates for research employment.

- Publications and papers:

The results are displayed on the web by each Laboratory and Department carrying out the tasks. In the attachment, the full list of our publications is included.

There are separate  research  and management issues related to the Multimedia actions.  We have been developing and working on new multi-user  multimedia communication  systems, as a special research task, in which we closely cooperate with the  standardization bodies  responsible for the telecommunications,  and implementing  a joint – virtual laboratory with the University of  Klagenfurt, Austria.

Several actions, visiting scientists, twinning steps are listed in the appended documents.

Workpackage progress report for Workpackage No.: C

Foreign visitors at the SZTAKI, virtual laboratories

- Objectives and planned actions:

The objectives are to invite foreign experts, and make their visits useful both for them and for the hosting partners.

There were around 430 foreign visitors at MTA SZTAKI since the  opening of the Centre of Excellence program. Some key persons, professors are listed among the special partners, detailed at the reports of the individual laboratories and WP  leaders. Some had only a single day or a few days with  us, and around 20 of them could stay with us for a longer period  Those  visitors’ travel costs  were financed by other sources, not from the CoE contract.

Here we just list the  long-term visitors,  who  won the  award from MTA SZTAKI – Centre of Excellence, after a  selection process for the submitted  applications:

| Long-term Visitor’s name | Time of visit | Related thematic WP |
| --- | --- | --- |
| Dr. Roland Tetzlaff, Frankfurt | May-Aug-2001 | WP3 |
| Prof. Serge Monchaud, Paris | July-Aug.-2001 | WP7+8 |
| Dr. Ronald Anton Scheidl, Vienna | July-Sept.2001 | WP 10 |
| Dr. Dragan Stokits, Bremen | Aug.-Oct.-2001 | WP 7 |
| Prof. Hakan Hjalmarsson, Sweden | Aug.-Oct.-2001 | WP 6 |
| Dr. Ulrich Meyer, Saarbrucken | Jan.-Febr.-2002 | WP6 |
| Ph.D. Alexandru Popa, Bucharest | Jan.-Febr.-2002 | WP8-C |
| Dr. Daniel Dochev, Sofia | Febr.-April-2002 | WP 2, C |
| Dr. Radoslav Pavlov, Sofia | Febr.-April-2002 | WP 2, C |
| Dr. Markus Holzer, Germany | March-April-2002 | WP 5 |
| Prof. Nick Bottka, U.K. | May-July-2002 | WP3 |
| Dr, Marco Gilli, Italy | July-Aug.-2002 | WP3 |
| Ph.D. Mauric ter Beek | March-Dec. 2002 | WP5 |
| Prof. Victor Mitrana, Spain | Sept.-Oct.-2002 | WP5 |
| Dr. Zsofia Ruttkay, Amsterdam | Sept.-Nov.-2002 | WP3 |
| CarlosManuel Dom.Matas, Seville | Oct.-Dec.-2002 | WP3 |
| Ph.D. Christian Mönch, | Jan.-Nov.-2003 | WP10 |
| Prof. Laurence Carassus, Paris | June-July, 2003 | WP9 |
| Ph.D. DavidLopez Villarino, Spain | June-Aug. 2003 | WP3 |
| Dr. Patrick Goverts, Belguim | Nov.-Jan.2004 | WP |
| Dr. Sandi Ferret, Paris | Oct.-Dec.2003 | WP6 |
| Dr. Miklos Santha | Oct.-Dec.2003 | WP6 |
| Dr. Daniel Dochev, Sofia | Nov. 03-Febr.2004 | WP 11 |
| Dr. Radoslav Pavlov, Sofia | Nov. 03-Febr.2004 | WP 11 |
| Ph.D. DavidLopez Villarino, Spain | Sept-Dec. 2003 | WP3 |
| Ph.D. Arpad Harangozo, Bucharest | Oct.-Dec.2003 | WP2 |
| Ph.D. Costin Cosouis, Bucharest | Oct.-Dec.2003 | WP2 |
| Ph.D. Renaud Peteri, Paris, Nizza | Jan.-Febr,(-Sept) | WP2-11 |

- Problems encountered:

It was a problem to re-invite visiting scientists. It takes a rather long time (might take a year) for persons to schedule a long research visit at any place, not just at SZTAKI.

- Results:

We have opened the invitation and advertised it to many partner institutions. We clarified the workplan with those we had selected for acceptance.

At the beginning and at the end of the visits we organised open seminars, inviting our academic and industrial partners as well, to take part in the meetings

We have prepared posters and slide-shows for demonstrating our Centre of Excellence at several exhibitions, universities when trying to attract young undergraduates and postgraduates for research employment.

Regarding the establishment of virtual laboratories, the RENED initiative was established between MTA SZTAKI (HU), INSA Rennes(F), TU Sofia (BG), ICMET and TU Craiova (RO), TU Kharkiv and Tavrichestiy National University (Ukr) in the filed of IT.

The VIMINS initiative for virtual institutes/laboratories  had its technical meeting in January, in Budapest.

The visiting scientists have their reports appended to this periodic report,

But they are publicly available to download/read at

www.sztaki.hu   clicking on the Centre of Excellence logo, or directly at:

http://www.sztaki.hu/sztaki/coe/

- Publications and papers:

There are a large number of publications and presentation slides. Not all papers can be attached or appended to this report, but most of them are downloadable from the web site:

http://www.sztaki.hu/sztaki/coe/

- Deliverables:

There is a significant increase in the networking among centres.  The large number of submitted proposals   is a good example of the activities of the MTA SZTAKI researchers.

The importance of the Institute has also increased, by the involvement of the  foreign  invited scientists, new ideas and   topics for research emerged.  The most  relevant increase in scope has been achieved by Prof. Roska, WP3,  by  introducing a BIONICS  interdisciplinary  scientific filed.  MTA SZTAKI  plays  the driving and key  role in the establishment of this new, cross-Hungarian  action.

Workpackage progress report for Workpackage No.: D

Organising Workshops, Conferences and Scientific Meetings

- Objectives and planned actions:

The driving force for this workpackage is to enable the widespread dissemination of the ideas, theories, methods and technologies. We had planned a large number of activities like this in most technical workpackages.

.

- Problems encountered:

The conferences and workshops we listed in the original proposal were already completed by the time we received the signed contract.

The Conferences  had  suffered from the effects of 11. September, as many participants had cancelled their business travel. By 2004 we can witness a positive change, and conferencing with personal attendance (not via videoconferencing) might again  be booming.

- Results:

There  were about 50 conferences and workshops, seminars,   that MTA SZTAKI  had organized from the beginning of the CoE project. The full list will be  updated on the web, and here we refer only to the main events, that had been managed through the CoE  and the Thematic workpackages involved.

During the last 2 years, we can be proud to have organized the most  important scientific events in Hungary:

In  November 2003, The  World Science Forum   had its conference based on our organization. The Conference was broadcasted via our new videoconferencing arrangements also on the internet via the IP high-bandwidth systems.  450 participants  (mostly foreigners) from all over the world attended this event, and most countries delegated its top minister responsible for research.

Other very significant  conference  in 2003 was the  World-Wide-Web conference. We had 570 participants, more than half from abroad.

For our thematic workpackages, like WP3, WP4, WP 5, WP7, WP8,  the following conferences  were requiring our very intensive, scientific efforts:

- An IFAC  IMS  Workshop on Intelligent Manufacturing,

- The DCFS 2003,

- The IFAC Workshop on Conrol Applications,

- The ERCIM WG Conference on Constrains,

- International GRID Seminar in March-April,

- SW Technology and Distributed Systems, 2nd April,

- CBSNet workshop,  on 3-4 April ,

- MACHTECH exhibition and  EU R&D Workshop , dedicated to industrial machine industry,

- Two e-learning fora, ( in March and June) with a growing participation (90—110 participants)

- A Technology Assessment meeting in July,

- A GRID Tutorial in June,

Further events are detailed  at the thematic reports.

- Publications and papers:

Books, preprints, proceedings, and other documents related to our scientific events are available. Most of the events are stored on videotapes as well, and there were many pictures taken for electronic, multimedia reuse. The presentations are done in Microsoft PowerPoint slides, and these files are stored.

- Deliverables:

In the appended part of the report, we added only the selected, main references to the conferences and seminars, etc. we organized. Many papers are available for downloading from the web address. We have also  appended a list  of  scientific posts, where scientists from SZTAKI are shown with their  international scientific commitments. This shows, how our Centre of Excellence has increased in reputation.

Workpackage progress report for Workpackage No.: E

Visits to another research centre

- Objectives and planned actions:

The objective was to share the ideas and research results with colleagues around Europe. For deeper and longer consultations, it is not enough to utilise video-conferencing, but personal visits are needed.

The director and a deputy-director of the SZTAKI took part in the ERCIM top-level Conferences. ERCIM is the European Research Fora for our several prioritised scientific main interest, and hence our institute must  establish a strong working relation with other ERCIM members.

- Many colleagues, had chance to visit conferences, or EU universities and research places for shorter or longer periods, but their financing was not based on the Centre of Excellence funds.

- The following visits – relevant to the CoE project had been managed:

| Name of visited place | Name of visitor | Time |
| --- | --- | --- |
| Stockholm,Nizza, Vienna,Luxemburg, ERCIM Institutes | Dr. Peter Inzelt director Prof. L. Monostori ddir. | Each 6 month |
| Klagenfurt University | Hutter, Keul, Sarkozy, Haidegger, Sarvary | 3 occations, 2002 July, July2003, Oct.2003, |
| Edinburgh Univ. EUREKA FACTORY | Haidegger | 2001. Octber |
| Prague, E-EUROPE | Keul-Haidegger | Oct. 2002 |
| Thessaloniki University | Haidegger | 2002. Octber |
| Munchen TU. Twinning | Ivanyos, Nagy | May 2003 |
| Krakow Univ. | 16 persons form the CNN Department of WP3, Prof. Roska | Aug.31.-Sept.4. 2003 |
| CIMSI Supsimanno | Haidegger | Nov. 2003 |
| TU Eindhoven, TU Paris | Ronyai, Ivanyos | Oct.2003, |

- Problems encountered:

Several long-term visits were planned, but till now not all have been realised, due to changes in the starting time. Short visits are very often taken for most of the Laboratories, to widen the co-operation and run joint projects, but the needs for the trips come up very rapidly, and thus they cannot be planned long ahead.

- Results:

Intense activity exists between our Institute and other institutes.

Some members of our Laboratories are often invited by foreign partners to join for preparing new project proposals.

A list of the cc. 300 visits to foreign laboratories by MTA SZTAKI scientists  is available on demand.

Annexes

Appended to the Periodic Report for HUN-TING

May 2004.

Most of the Annexes  are also downloadable  from the web:

http://www.sztaki.hu/sztaki/coe/

A1. Final reports of visiting scientists. See list on following sheet

In Volume II:

A2. Research Tasks  undertaken

A3. Memberships in international scientific committees

A4. Publications in 2002,

A5. Publications in 2003

Annexes   not appended, but  accessible from the web at :

http://www.sztaki.hu/sztaki/coe/

These  parts are :

Publications –of visiting scientists, joint publications, etc.

Reports of Conferences, Workshops organized.